## Sheet1
Id (R/O) | External Id (R/O) | Title* | State* | Release | Data Source | Team | Comments | Risk | Dependency | Start Sprint | End Sprint
112866 | TANT-587 | UDPC - UDPR Migration - Marketing Refined Zone | 2 - In Progress | PI 12-A (10/12/2022-01/17/2023) | Marketing Refined | Anant | Do we have the data classification? |  |  | Sprint 3 | Sprint 3
112863 | TANT-600 | UDPC - UDPR Migration - Schema Evolution | 2 - In Progress | PI 12-A (10/12/2022-01/17/2023) | PX | Anant | This will be closed in PI12
120707 | TRAIL-503 | UDPC - UDPR Migration - Marketing Refined - Decommission in UDPC of the marketing refined data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Marketing Refined | Anant | This might get rollover to PI14 as this should happen post PX decomission |  |  | Sprint 6 | Sprint 6
120706 | TANT-691 | UDPC - UDPR Migration - Marketing Refined - Validation of the historical and incremental data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Marketing Refined | Anant |  |  |  | Sprint 4 | Sprint 4
120705 | TANT-690 | UDPC - UDPR Migration - Marketing Refined - User Migration for the Marketing refined data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Marketing Refined | Anant |  |  |  | Sprint 5 | Sprint 5
120365 | TRAIL-500 | UDPC - UDPR Migration - Preferences - Validation of historical and incremental Preferences data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Preferences | Trailblazers |  |  |  | Sprint 2 | Sprint 2
120364 | TRAIL-499 | UDPC - UDPR Migration - Salesforce - Validation of historical and incremental Salesforce data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Salesforce | Trailblazers |  |  |  | Sprint 2 | Sprint 2
120363 | TRAIL-498 | UDPC - UDPR Migration - CDP - Migrate Client Preferences required for Marketing (Split Part 2) | 2 - In Progress | PI 13-A (01/18/2023-04/11/2023) | Preferences | Trailblazers |  |  |  | Sprint 1 | Sprint 1
120362 | TRAIL-497 | UDPC - UDPR Migration - CDP - Migration of Salesforce Data (Split Part 2) | 2 - In Progress | PI 13-A (01/18/2023-04/11/2023) | Salesforce | Trailblazers |  |  |  | Sprint 1 | Sprint 1
120179 |  | UDPC - UDPR Migration - PX - Validation of historical and incremental PX data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | PX | Anant |  |  |  | Sprint 2 | Sprint 3
120178 |  | UDPC - UDPR Migration - Preferences - User migration for the Preferences data source | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Preferences | Trailblazers |  |  |  | Sprint 2 | Sprint 3
120177 |  | UDPC - UDPR Migration - Salesforce - User migration for the Salesforce data source | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Salesforce | Trailblazers |  |  |  | Sprint 2 | Sprint 3
120176 | TANT-686 | UDPC - UDPR Migration - PX - User migration for the PX data source | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | PX | Anant |  |  |  | Sprint 3 | Sprint 3
120173 | TANT-685 | UDPC - UDPR Migration - PX - Refined Data Migration | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | PX | Anant | Data Classification pending from Product |  |  | Sprint 2 | Sprint 2
120171 | TRAIL-494 | UDPC - UDPR Migration - Notifications - Refined Data Migration | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Notifications | Trailblazers
119039 | TRAIL-492 | UDPC - UDPR Migration - Notifications - Land Notifications Data (Split Part 2) | 2 - In Progress | PI 13-A (01/18/2023-04/11/2023) | Notifications | Trailblazers |  |  | MySQL support
119038 | TANT-680 | UDPC - UDPR Migration - PX - Land Planning (PX) Data (Split Part 2) | 2 - In Progress | PI 13-A (01/18/2023-04/11/2023) | PX | Anant | Saurav's question on data deletion. Assuming no new design changes. Asssuming Pydat pipeline creation happens later. |  |  | Sprint 1 | Sprint 1
118570 | TRAIL-495 | UDPC - UDPR Migration - Notifications - Decommission in UDPC of notifications data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Notifications | Trailblazers
118569 | TRAIL-496 | UDPC - UDPR Migration - Notifications - Validation of historical and incremental notifications data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Notifications | Trailblazers
118518 | TANT-670 | UDPC - UDPR Migration - Contact Center - Land Contact center data in UDPR | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Contact Center | Anant | Do we have the data classification? This should be a Stretch Objective
118517 | TRAIL-453 | UDPC - UDPR Migration - DI Claims - Land DI claims data in UDPR | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | DI Claims | Trailblazers | Do we have the data classification? This should be a Stretch Objective
118513 | TRAIL-456 | UDPC - UDPR Migration - Salesforce - Decommissioning of Salesforce data | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Salesforce | Trailblazers |  |  |  | Sprint 5 | Sprint 6
118512 | TRAIL-455 | UDPC - UDPR Migration - Preferences - Decommission of Preferences data source | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Preferences | Trailblazers |  |  |  | Sprint 5 | Sprint 6
118511 | TANT-672 | UDPC - UDPR Migration - PX - Decommission of PX data in UDPC | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | PX | Anant | This might get rollover to PI14 as the data size is huge to decommission in UDPC |  |  | Sprint 5 | Sprint 6
118510 | TRAIL-454 | UDPC - UDPR Migration - Notifications - User migration for the notifications data source | 0 - Pending Approval | PI 13-A (01/18/2023-04/11/2023) | Notifications | Trailblazers
120381 | TANT-688 | UDPC - UDPR Migration - Contact center - User migration for the Contact center data source | 0 - Pending Approval | PI 14-A (04/12/2023-07/18/2023) | Contact Center
120380 | TRAIL-502 | UDPC - UDPR Migration - DI claims - User migration for the DI claims data source | 0 - Pending Approval | PI 14-A (04/12/2023-07/18/2023) | DI Claims
120367 | TANT-687 | UDPC - UDPR Migration - Contact center - Validation of historical and incremental Contact center data | 0 - Pending Approval | PI 14-A (04/12/2023-07/18/2023) | Contact Center
120366 | TRAIL-501 | UDPC - UDPR Migration - DI Claims - Validation of historical and incremental DI data | 0 - Pending Approval | PI 14-A (04/12/2023-07/18/2023) | DI Claims
118516 | TANT-671 | UDPC - UDPR Migration - Contact Center - Decommission of Contact center data | 0 - Pending Approval | PI 14-A (04/12/2023-07/18/2023) | Contact Center
118515 | TRAIL-457 | UDPC - UDPR Migration - DI Claims - Decommission of DI Claims data | 0 - Pending Approval | PI 14-A (04/12/2023-07/18/2023) | DI Claims